## SUPS-WRKS-NCONS
PROCUREMENT PLAN FOR GOODS, WORKS AND NON CONSULTANCY SERVICES - FOR SUBMISSION TO TREASURY, PPDA and PUBLICATION
Procuring and Disposing Entity: |  |  |  | NANSANA MUNICIPAL COUNCIL
Financial Year: |  | 2025-2026
S/No | Subject of procurement | Currency | Estimated cost | Multi-year procurement (where applicable) |  |  |  |  | Source of funding | Procurement method | Procurement Category | Contract Type | PRE-QUALIFICATION (Yes or No) | Apply Reservation Scheme (Yes/No) | Apply Reservation Scheme (Local Providers, Special Interest Groups) | INVITATION AND AWARD OF BIDS |  |  |  | Contract signing date | Completion date
|  |  |  | Current year's estimated cost | Projected completion time (in years) | Paid up sum | Pending sum | Pending time to completion | [7 empty] | Bid invitation date | Bid closing/ Opening date | Approval evaluation report date | Award notification date
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22
1 | Maintenance of football pitch of Kanyange PS for Nabweru division | UGX | 49820500 | [5 empty] | Internally Generated Funds | Quotations Method | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-29 | 2025-12-29 | 2026-06-30
2 | Supply and installation of street solar lights for Nabweru division | UGX | 20000000 | [5 empty] | Government Of Uganda | Micro Procurement | Works | Ad Measurement Contracts | Yes | Yes | Local Providers | 2026-01-08 | 2026-01-14 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-06-30
3 | Renovation of Maganjo Health Centre II OPD Ward facilitiesfor Nabweru division | UGX | 30929982 | [5 empty] | Government Of Uganda | Quotations Method | Works | Ad Measurement Contracts | Yes | Yes | Local Providers | 2026-01-08 | 2026-01-14 | 2026-01-30 | 2026-02-10 | 2026-02-18 | 2026-06-30
4 | Routine mechanized maintenance and culvert installation for;-Energo kikajjo, -kanyogoga mayanja road, -Karimujjabo road | UGX | 182544959 | [5 empty] | Government Of Uganda | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-29 | 2025-12-29 | 2026-06-30
5 | supply of operational fuel and lubricants for Nabweru division | UGX | 41699436 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
6 | Construction of an office block Phase I in Nabweru division | UGX | 295000000 | [5 empty] | Government Of Uganda | Quotations Method | Works | Ad Measurement Contracts | Yes | Yes | Local Providers | 2025-09-03 | 2025-09-09 | 2025-09-23 | 2025-11-10 | 2025-11-11 | 2026-06-30
7 | Procure of 3-seater wooden desks with metallic stands for schools for Nansana division | UGX | 35000000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-10-22 | 2025-11-04 | 2025-11-10 | 2026-01-27 | 2026-01-27 | 2026-06-30
8 | Procure of furniture for various offices and a notice board for Nansana division | UGX | 20000000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-01-08 | 2026-01-14 | 2026-01-30 | 2026-02-10 | 2026-02-20 | 2026-06-30
9 | Fencing of Kawanda HCIII | UGX | 70000000 | [5 empty] | Internally Generated Funds | Quotations Method | Works | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-01-08 | 2026-01-14 | 2026-01-30 | 2026-02-10 | 2026-02-18 | 2026-06-30
10 | supply of operational fuel and lubricants for Nansana Division | UGX | 96370433 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
11 | Light Grading and stone pitching /gravel fill of Mwebe division roads; -Glory Buddo Church of Uganda in 7/8 -Kafunda-Kabira Rd in Nabweru South -Katongole Sebuliba,Kazo Central High School -Bujagali Road -Valley View Wampamba rd in Nansana West | UGX | 306335089 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
12 | Procurement of day-old multipurpose chicks/drugs/feeds and piglets of 120-150 days for Nansana division | UGX | 30000000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-10-22 | 2025-10-28 | 2025-11-10 | 2025-11-20 | 2025-11-20 | 2025-12-02
13 | Provision of a base and supply of a 10,000 litres capacity water tank for Nansana SDA P/s | UGX | 10837000 | [5 empty] | Government Of Uganda | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-10-23 | 2025-10-29 | 2025-11-10 | 2025-11-25 | 2025-12-02 | 2026-02-17
14 | Renovation of a 3 (three) classroom block at St. Stephen C/U P/s | UGX | 77229704 | [5 empty] | Government Of Uganda | Quotations Method | Works | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-10-23 | 2025-10-29 | 2025-11-10 | 2025-11-25 | 2025-12-02 | 2026-02-17
15 | Supply of two hundred (250) school desks for selected schools | UGX | 75000000 | [5 empty] | Government Of Uganda | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-10-22 | 2025-11-04 | 2025-11-10 | 2026-01-27 | 2026-01-27 | 2026-06-30
16 | supply of operational fuel and lubricants for Gombe Division | UGX | 36524305 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
17 | Procurement of fuel/Road materials/equipment for grading the selected roads - Busikiri-Kyambizzi-Kitungwa Ps (4.3km) road - Christ the King Kasalirwe (from World ahead) Road - Lakeeri – Bombo Road (4.0km) - Namakonkome - Buwambo Seed school - Ssenga – Boarder – Kasso (2.0km) road - St Loza - Kirwanira (1.5km) road - World ahead - Kibungo road (2.0km) | UGX | 154598753 | [5 empty] | Government Of Uganda | Open Domestic Bidding | Supplies | Framework Contracts | Yes | Yes | Local Providers | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-09-10 | 2025-09-10 | 2026-06-30
18 | Construction of a 5-Stance lined latrine at Gombe P/S | UGX | 36000000 | [5 empty] | Internally Generated Funds | Quotations Method | Works | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-10-23 | 2025-10-29 | 2025-11-10 | 2025-11-20 | 2025-11-21 | 2026-06-30
19 | Completion of a wall fence phase II at Nansana HCII | UGX | 68407557 | [5 empty] | Government Of Uganda | Quotations Method | Works | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-10-23 | 2025-10-29 | 2025-11-10 | 2025-11-20 | 2025-12-02 | 2026-06-30
20 | Procurement of 200(two) hundred 3 –seater wooden school desks with metallic stands for various Schools | UGX | 60000000 | [5 empty] | Government Of Uganda | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-10-22 | 2025-11-04 | 2025-11-10 | 2026-01-27 | 2026-01-27 | 2026-06-30
21 | Construction of a Public 5 lined pit latrine at Kiwenda New Primary School and at Nakyesanja Daily Market | UGX | 74441834 | [5 empty] | Internally Generated Funds | Quotations Method | Works | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-01-08 | 2026-01-14 | 2026-01-30 | 2026-02-17 | 2026-02-18 | 2026-06-30
19 | Grading and Maintenance of roads-fuel and hire of road equipment, community sensitization: 1. Busukuma - Seeta-Kabumba Road (4km) 2. Nabitalo-Springfield-Gguludene-Ntinda Road (6km) 3. Nakakololo-Lugo-Banda-Kabonge Road (7km) 4. Namawata - Butera Road (2km) | UGX | 160773418 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
20 | Construction of 3(three) units of 5(five) stances Lined Latrines each at; -Busukuma C.O.U P/S -Busikiri Moslem P/s | UGX | 70000000 | [5 empty] | Government Of Uganda | Quotations Method | Works | Ad Measurement Contracts | Yes | Yes | Local Providers | 2025-11-12 | 2025-11-18 | 2025-12-19 | 2026-01-12 | 2026-01-12 | 2026-06-30
21 | supply of operational fuel and lubricants for Education Department | UGX | 180000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
22 | supply of stationery for examination papers | UGX | 15000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
23 | Purchase of assorted office furniture for Education department | UGX | 47365200 | [5 empty] | Government Of Uganda | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-03-25 | 2026-03-31 | 2026-04-14 | 28/4/2026 | 13/5/2026 | 2026-06-30
24 | construction of School Facilities at; - St. Mark Kakerenge -Damalie Nabagereka | UGX | 220000000 | [5 empty] | Government Of Uganda | Quotations Method | Works | Ad Measurement Contracts | Yes | Yes | Local Providers | 2025-11-12 | 2025-11-18 | 2025-12-19 | 2026-02-20 | 2026-02-20 | 2026-06-30
25 | Procure of 3-seater wooden desks with metallic stands for schools | UGX | 192550000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-10-22 | 2025-11-04 | 2025-11-10 | 2026-01-27 | 2026-01-27 | 2026-06-30
26 | supply of operational fuel and lubricants for Planning Unit | UGX | 75000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
27 | fuel, maintenance ,service and repair of Vehicles for works | UGX | 80000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
28 | Procurement of Mechanized maintenance of 166.5km on various roads and stone pitching of 6.2km on Eastern Ring Road | UGX | 1684146761 | [5 empty] | Government Of Uganda | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-06-10 | 2025-06-23 | 2025-07-07 | 2025-07-18 | 2025-07-24 | 2026-06-30
29 | Upgrading of Dick Kaweesa Road 1.6km to Bitumen Standards in Nansana Municipality | UGX | 8155252996 | [5 empty] | Donor | Open Domestic Bidding | Works | Lumpsum Contracts | No | No | N/A | 2025-05-22 | 2025-07-03 | 2025-08-08 | 2025-09-18 | 2025-11-24 | 2026-06-30
30 | Consultancy services for environment and social safeguard supervision for the construction and upgrading of Dick Kaweesa Road 1.6km to Bitumen Standards in Nansana Municipality | UGX | 514397500 | [5 empty] | Donor | Open Domestic Bidding | Consultancy Services | Lumpsum Contracts | No | No | N/A | 2025-05-22 | 2025-07-02 | 2025-10-10 | 2025-11-21 | 2025-11-24 | 2026-06-30
31 | Consultancy services for Engineering Supervision for the construction and upgrading of Dick Kaweesa Road 1.6km to Bitumen Standards in Nansana Municipality | UGX | 1022795000 | [5 empty] | Donor | Open Domestic Bidding | Consultancy Services | Lumpsum Contracts | No | No | N/A | 2025-05-22 | 2025-07-02 | 2025-10-10 | 2025-11-21 | 2025-12-02 | 2026-06-30
32 | Phase 2 of Upgrade of Busukuma-Nagamba-Kasozi Rd of 1.1km | UGX | 2385000000 | [5 empty] | Government Of Uganda | Open Domestic Bidding | Works | Ad Measurement Contracts | No | Yes | Local Providers | 2026-08-26 | 2025-09-15 | 2025-10-20 | 2025-12-22 | 2025-12-22 | 2026-06-30
33 | Construction of a box culvert at the spot connecting to Katooke- Kisimu | UGX | 265000000 | [5 empty] | Government Of Uganda | Open Domestic Bidding | Works | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-11-12 | 2025-11-18 | 2025-12-19 | 2026-02-20 | 2026-02-23 | 2026-06-30
34 | Construction of a box culvert at Kidokolo | UGX | 265000000 | [5 empty] | Government Of Uganda | Open Domestic Bidding | Works | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-11-12 | 2025-11-18 | 2025-12-19 | 2026-02-20 | 2026-02-23 | 2026-06-30
35 | Pot hole Patching on selected roads | UGX | 90000000 | [5 empty] | Government Of Uganda | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-06-10 | 2025-06-23 | 2025-07-07 | 2025-07-18 | 2025-07-24 | 2026-06-30
36 | Provision of Consultancy Services for the selected road designs | UGX | 50000000 | [5 empty] | Government Of Uganda | Quotations Method |  |  | Yes | Yes | Local Providers | 2026-03-25 | 2026-03-31 | 2025-10-27 | 2025-12-03 | 2025-12-06 | 2026-06-30
37 | Completion of second floor at Annex Building | UGX | 300000000 | [5 empty] | Internally Generated Funds | Quotations Method | Works | Ad Measurement Contracts | Yes | Yes | Local Providers | 2026-01-08 | 2026-01-14 | 2026-01-30 | 2026-03-12 | 2026-03-13 | 2026-06-30
38 | supply of operational fuel and lubricants for Health department | UGX | 10000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
39 | vehicle maintenance | UGX | 28000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
40 | Collection of solid and medical waste | UGX | 30072000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Ad Measurement Contracts | Yes | Yes | Special Interest Groups | 2025-10-07 | 16/7/2025 | 2025-08-12 | 2025-09-01 | 2025-01-10 | 31/9/2026
41 | Completion works of Matugga HCIII | UGX | 209000000 | [5 empty] | Donor | Quotations Method | Works | Ad Measurement Contracts | Yes | Yes | Local Providers | 2025-11-12 | 2025-11-18 | 2025-12-19 | 2026-04-01 | 2026-04-01 | 2026-06-30
42 | Procurement of assorted furniture for Nabweru Health Centre III | UGX | 79680000 | [5 empty] | Government Of Uganda | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-03-25 | 2026-03-31 | 2026-04-14 | 28/4/2026 | 13/5/2026 | 2026-06-30
43 | vehicle maintenance | UGX | 14000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
44 | office stationery for Administration | UGX | 8000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
45 | Procurement of furniture for Administration department | UGX | 15000000 | [5 empty] | Government Of Uganda | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-03-25 | 2026-03-31 | 2026-04-14 | 2025-12-03 | 2025-12-06 | 2026-06-30
46 | fuel oil and lubricants for Finance and Administration | UGX | 136000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
47 | Property Rates in four divisions of Nansana Municipality | UGX | 5006160500 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Non-Consultancy Services | Ad Measurement Contracts | Yes | Yes | Local Providers | 2025-05-27 | 2025-06-20 | 2025-06-26 | 2025-07-10 | 2025-07-10 | 2026-06-30
48 | Local service Tax | UGX | 1205499000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Non-Consultancy Services | Ad Measurement Contracts | Yes | Yes | Local Providers | 2025-05-27 | 2025-06-20 | 2025-06-26 | 2025-07-10 | 2025-07-10 | 2026-06-30
49 | Vehicle Parking Fees | UGX | 124265000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Non-Consultancy Services | Ad Measurement Contracts | Yes | Yes | Local Providers | 2025-05-27 | 2025-06-20 | 2025-07-15 | 2025-12-03 | 2025-08-18 | 2026-06-30
50 | Public Health Licences / other Licenses | UGX | 148000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Non-Consultancy Services | Ad Measurement Contracts | Yes | Yes | Local Providers | 2025-08-26 | 2025-09-15 | 2025-10-20 | 2025-11-06 | 2025-11-11 | 2026-06-30
51 | fuel oil and lubricants for production | UGX | 25000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
52 | Procurement of Agricultural Supplies | UGX | 50000000 | [5 empty] | Government Of Uganda | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-10-22 | 2025-10-28 | 2025-11-10 | 2025-11-20 | 2025-11-20 | 2025-12-02
53 | fuel oil and lubricants for Community based services | UGX | 28000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
54 | Procurement of printing, binding and hard covering services | UGX | 52500000 | [5 empty] | Government Of Uganda | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-03-03 | 2026-03-09 | 2026-03-18 | 2026-04-10 | 2026-04-10 | 2026-06-30
55 | fuel oil and lubricants for Natural resources | UGX | 10000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Works | Framework Contracts | Yes | Yes | Local Providers | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 2026-06-30
56 | Provision of Consultancy Services for the preparation of the Physical detailed Plan for Lugo ward and Gombe ward | UGX | 199976296 | [5 empty] | Donor | Quotations Method | Consultancy Services | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-11-12 | 2025-11-18 | 2026-01-30 | 2026-02-10 | 2026-02-10 | 2026-06-30
57 | Provision of development of digital road inventory for Gombe and Busukuma Divisions | UGX | 199990000 | [5 empty] | Donor | Quotations Method | Consultancy Services | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-11-12 | 2025-11-18 | 2026-01-30 | 2026-02-10 | 2026-02-17 | 2026-06-30
58 | Provision and installation of concrete pillars on various roads | UGX | 96204960 | [5 empty] | Government Of Uganda | Quotations Method | Works | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-03-03 | 2026-03-09 | 2026-03-18 | 2026-04-10 | 2026-04-10 | 2026-06-30
59 | Provision of Consultancy Services for the production of a status survey report and costed operation and maintenance strategy | UGX | 24000000 | [5 empty] | GOU and Donor | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | Yes | Yes | Local Providers | 23/4/2026 | 29/4/2026 | 2026-12-06 | 17/6/2026 | 17/6/2026 | 2026-06-30
60 | Provision of Valuation of properties and updating Revenue Registers with proper Business Location details,building names,GIS Coordinates on IRAS and Nansana GIS Database | UGX | 340218987 | [5 empty] | GOU and Donor | Quotations Method | Consultancy Services | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-01-08 | 2026-01-23 | 2026-03-18 | 25/5/2026 | 25/5/2026 | 2026-06-30
61 | Procurement of 292 Smart Waste Bins within Nabweru and Nansana divisions | UGX | 119933100 | [5 empty] | GOU and Donor | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-01-08 | 2026-01-14 | 2026-01-30 | 2026-02-10 | 2026-02-17 | 2026-06-30
62 | Provision of Consultancy Services in production of a Wetland restoration strategy and 1(one) Wetland Action Plan | UGX | 200000000 | [5 empty] | GOU and Donor | Quotations Method | Consultancy Services | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-11-12 | 2025-11-18 | 2026-01-30 | 2026-02-10 | 2026-02-13 | 2026-06-30
63 | Procurement of 2(two) noise meters, Water and Air Quality Monitors | UGX | 79000000 | [5 empty] | GOU and Donor | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2025-11-12 | 2025-11-18 | 2025-12-19 | 2026-01-12 | 2026-02-12 | 2026-06-30
64 | Procurement of 1(one) Noise metre | UGX | 31466500 | [5 empty] | GOU and Donor | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-04-23 | 2026-04-29 | 2026-05-08 | 2026-05-28 | 2026-05-29 | 2026-06-30
65 | Establishment of 1(one) Tree Nursery Bed and related facilities | UGX | 153040000 | [5 empty] | Donor | Quotations Method | Works | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-03-25 | 2026-03-31 | 2026-04-14 | 2026-04-28 | 2026-04-28 | 2026-06-30
66 | Procurement of 10(ten) desktop computer sets and provision of Intercom Set up | UGX | 55000000 | [5 empty] | Donor | Quotations Method | Supplies | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-03-03 | 2026-03-09 | 2026-03-18 | 2026-04-10 | 2026-04-10 | 2026-06-30
67 | Development of Nansana Municipal Data Management Intergrated System | UGX | 32800000 | [5 empty] | GOU and Donor | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-03-25 | 2026-03-31 | 2026-04-14 | 2026-04-28 | 2026-04-28 | 2026-06-30
68 | construction of institutional energy saving stoves | UGX | 42142756 | [5 empty] | GOU and Donor | Quotations Method | Works | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-03-25 | 2026-03-31 | 2026-04-14 | 2026-04-28 | 2026-04-28 | 2026-06-30
69 | Provision of temporary site for accomodation of Nansana Daily Market Vendors | UGX | 288000000 | [5 empty] | GOU and Donor | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2026-03-03 | 2026-03-09 | 2026-03-18 | 2026-06-18 | 2026-06-19 | 2026-06-30
70 | Provision of Consultancy Services for the provision of Documentary of Nansana Investment Profile | UGX | 20294156 | [5 empty] | GOU and Donor | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | Yes | Yes | Local Providers | 2026-03-03 | 2026-03-09 | 2026-03-18 | 2026-06-18 | 2026-06-19 | 2026-06-30
| TOTAL |  | 26604263682
| Prepared by |  | Name:
Signature:
|  |  | Designation: | Head PDU
Date:
| Approved by |  | Name:
Signature:
|  |  | Designation: | Accounting Officer
Date:

## SUPS-WRKS-NCONS-internal use
PROCUREMENT PLAN FOR GOODS, WORKS AND NON-CONSULTANCY SERVICES - INTERNAL USE
Name of Procuring Entity:
Financial Year:
S/No. | Subject of Procurement | Plan vs. Actual | Currency | Baisc Data | [9 empty] | Pre-qualification | [7 empty] | Invitation for Bids and Evaluation |  |  |  |  | Contract Finalization
[14 empty] | Document |  | Invitation Date |  | Evaluation |  | Bidding Documents |  | Invitation for Bidding |  | Bid Evaluation and Contract Award
|  |  |  | Estimated Cost | Multi-year procurement (where applicable) |  |  |  |  | Source of Funding | Procurement Method | Apply Reservation Scheme (Yes/No) | Apply Reservation Scheme: Local Providers, Special Interest Groups | Preparation by PDU and CC submission | Approval by CC | Invitation Date | Closing-Opening | Submission Evaluation Report | Approval by CC | Prep & Submission by PDU | Approval by CC | Bid Invitation Date | Bid Closing-Opening | Submission Bid Evaluation Report | Approval by CC | Approval by SG | Contract Signature Date | Completion Date
|  | Plan |  |  | Current year's estimated cost | Projected completion time (in years) | Paid up sum | Pending sum | Pending time to completion
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
| Prepared by |  |  | Name:
Signature:
|  |  |  | Designation: | [5 empty] | Procurement Officer
Date:
| Approved by |  |  | Name:
Signature:
|  |  |  | Designation: | [5 empty] | Head PDU
Date:

## Consultancy
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - FOR SUBMISSION TO THE SECRETARY TO TREASURY, PPDA AND PUBLICATION
Procuring and Disposing Entity:
Financial Year:
S/No | Subject of procurement | Currency | Estimated cost | Multi-year procurement (where applicable) |  |  |  |  | Source of funding | Procurement method | Procurement Type | Apply Reservation Scheme (Yes/No) | Apply Reservation Scheme: Local Providers, Special Interest Groups | Contract type | Request for Expression of Interest |  |  |  | Invitation of proposals and approval for award |  |  |  |  | Completion date
|  |  |  | Current year's estimated cost | Projected completion time (in years) | Paid up sum | Pending sum | Pending time to completion | [6 empty] | Invitation of Expressions of Interest date | Closing-Opening date | Approval of shortlist | Notification date | Invitation of proposals date | Submission/ opening date | Approval of final evaluation report | Notification date | Contract signing date
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25
| Prepared by |  | Name: | [11 empty] | Approved by | Name
|  |  | Signature: | [12 empty] | Signature:
|  |  | Designation: | [12 empty] | Designation:
|  |  | Date: | [12 empty] | Date:

## Consultancy - Internal use
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - INTERNAL USE
Name of the Procuring Entity:
Financial Year:
S/No. | Subject of Procurement | Plan vs. Actual | Basic Data | [10 empty] | Request for Expression of Interest |  |  |  | Preparation of RFP Documents |  | Invitation of proposals and approval for award | [6 empty] | Contract Finalization
|  |  | Estimated Cost and Currency | Multi-year procurement (where applicable) |  |  |  |  | Procurement Method | Selection Method | Contract Type |  |  | Invitation |  | Evaluation |  |  |  | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F)
[12 empty] | Apply Reservation | Apply Reservation Scheme: Local Providers, Special Interest Groups | Invitation Date | Closing-Opening | Submission Evaluation Report | Approval of Shortlist | Prep & Submission by PDU | Approval by CC | Invitation Date | Submission/ Opening Date | Submission Evaluation Report | Approval of Technical Evaluation Report. | Opening Financial Proposals | Submission of Final Evaluation Report | Approval EvaluationReport | Contract Award Date | SG approval | Contract Signature Date
|  |  |  | Current year's estimated cost | Projected completion time (in years) | Paid up sum | Pending sum | Pending time to completion
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
| Prepared by |  | Name:
Signature:
Designation:
Date:
| Approved by |  | Name:
Signature:
Designation:
Date:

## User guiding notes
Note 1
Where they have been used, the following abbreviations stand for;
PDU - Procurement and Disposal Unit
SUPS - Supplies
NCONS - Non-consultancy Services
CONS - Consultancy Services
WRKS -Works
FY - Financial Year
Note 2
There are 2 templates, the first being for supplies, works, non-consultancy services and the second being for consultancy services. All fields in the templates to be submitted should be accurately completed
Note 3
The templates for internal use are for the PDU's tracking purposes and should not be submitted
Note 4
The multi-year procurement field should only be used for procurements whose projected completion time is to exceed one FY. And where the contract is in its subsequent years of implementation, the plan should be completed to indicate the completed and pending time/funding to contract completion.
Note 5
This template should be used in line with Sections 34(2), 58 of the PPDA Act and the PPDA (Procurement Planning) Regulations, 2023
Note 6
The approved plan should be submitted to the Treasury, PPDA and published by 31st July
For any clarification about the plan template or related issues reach out on;
compliance@ppda.go.ug
or call 0414311100